## Sheet1
Hours Worked Per Day
Tasks - ITERATION 2 | Duration (Days) | Starting Date | Assigned To | Reviewed By | Ending Date | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Send email confirmation after reminder is created | 1 | 2015-09-29 | Alexander | bar: Hours Worked Per Day 29 to Hours Worked Per Day 8
Upload picture (optional) | 3 | 2015-10-01 | Glenn
Send email confirmation after account is created | 1 | 2015-09-29 | Alexander
Edit your reminders | 3 | 2015-09-17 | Alexander | Fixed: Glenn |  | Hours Worked Per Day 29: 2
Mark the added row green for 3 seconds. | 1 | 2015-09-29 | Glenn | bar: Hours Worked Per Day 29 to Hours Worked Per Day 8
Send email confirmation after reminder is editted | 1 | 2015-09-29 | Alexander
Send email confirmation after reminder is deleted | 1 | 2015-09-29 | Alexander
Mark the added row green for 3 seconds. | 1 | 2015-09-29 | Glenn | bar: Hours Worked Per Day 29 to Hours Worked Per Day 8
Create a reminder for a friend | 0
Enter email address | 0
Select reminder frequency (daily, weekly, monthly, one-time) | 0
Enter reminder text | 0
Select date for first email | 0
Display message after reminder is created | 0 | [14 empty] | Color codes
Send email confirmation after reminder is created | 0 | [14 empty] | Finished
View your friends reminders | 0 | [14 empty] | In Progress
Reminder frequency | 0 | [14 empty] | Unreviewed
Reminder text | 0
Date for first email | 0
Format all emails so they look like a webpage | 0
Allow reminders to be created, editted, and deleted only after an account has been created and the user has signed into Reminder | 0
Display user's email address and picture after he has signed into Reminder | 2 | Glenn
'