## Sheet1
Hours Worked Per Day
Tasks - ITERATION 2 | Duration (Days) | Starting Date | Assigned To | Reviewed By | Ending Date | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Send email confirmation after reminder is created | 1 | 2015-09-29 | Alexander | Both |  | Hours Worked Per Day 29: 1; Hours Worked Per Day 5: 0,5; Hours Worked Per Day 6: 0,5
Upload picture (optional) | 3 | 2015-10-01 | Glenn | Both |  | Hours Worked Per Day 6: 2
Send email confirmation after account is created | 1 | 2015-09-29 | Alexander | Both |  | Hours Worked Per Day 5: 0,5; Hours Worked Per Day 6: 0,5
Edit your reminders | 3 | 2015-09-17 | Alexander | Both |  | Hours Worked Per Day 29: 2
Mark the added row green for 3 seconds. | 1 | 2015-09-29 | Glenn | Both | bar: Hours Worked Per Day 29
Send email confirmation after reminder is editted | 1 | 2015-09-29 | Alexander | Both |  | Hours Worked Per Day 5: 0,5; Hours Worked Per Day 6: 0,5
Send email confirmation after reminder is deleted | 1 | 2015-09-29 | Alexander | Both |  | Hours Worked Per Day 5: 0,5; Hours Worked Per Day 6: 0,5
Mark the added row green for 3 seconds. | 1 | 2015-09-29 | Glenn | Both | bar: Hours Worked Per Day 29
Create a reminder for a friend | 2 | 2015-10-05 | Glenn | Both | bar: Hours Worked Per Day 5 to Hours Worked Per Day 6
Enter email address | 2 | 2015-10-05 | Glenn | Both
Select reminder frequency (daily, weekly, monthly, one-time) | 2 | 2015-10-05 | Glenn | Both
Enter reminder text | 2 | 2015-10-05 | Glenn | Both
Select date for first email | 2 | 2015-10-05 | Glenn | Both
Display message after reminder is created | 2 | 2015-10-05 | Glenn | Both | [11 empty] | Color codes
Send email confirmation after reminder is created | 2 | 2015-10-05 | Glenn | Both | [11 empty] | Finished
View your friends reminders | 1 | 2015-10-04 | Glenn | Both |  | Hours Worked Per Day 4: 1; Hours Worked Per Day 5: 1; Hours Worked Per Day 6: 2 | In Progress
Reminder frequency | 1 | 2015-10-04 | Glenn | Both | [11 empty] | Unreviewed
Reminder text | 1 | 2015-10-04 | Glenn | Both | [11 empty] | Finished Early
Date for first email | 1 | 2015-10-04 | Glenn | Both
Format all emails so they look like a webpage | 1 | 2015-10-06 | Alexander | Both |  | Hours Worked Per Day 6: 0,5
Allow reminders to be created, editted, and deleted only after an account has been created and the user has signed into Reminder | 1 | Finished in 1st Iteration |  | Both
Display user's email address and picture after he has signed into Reminder | 2 | Finished in 1st Iteration |  | Both
'