## Sheet1
Hours Worked Per Day
Tasks - ITERATION 1 | Duration (Days) | Starting Date | Assigned To | Reviewed By | Ending Date | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 19 | 23 | 24
Set up database | 1 | 2015-09-08 | Alexander | Unreviewed | 2015-09-11 | Hours Worked Per Day 8: 1,5
Set up project libraries and framework | 3 | 2015-09-08 | All | Unreviewed | 2015-09-14 | Hours Worked Per Day 8: 1,5; Hours Worked Per Day 11: 1,5; Hours Worked Per Day 14: 1,5
Create mock design | 1 | 2015-09-15 | Glenn | Unreviewed | 2015-09-15 | bar: Hours Worked Per Day 15
Set up database test data | 1 | 2015-09-14 | Alexander | Unreviewed | 2015-09-15 | Hours Worked Per Day 12: 1,5
Create a reminder to yourself |  | 2015-09-13 | Glenn | Unreviewed | bar: Hours Worked Per Day 13; Hours Worked Per Day 17
Select reminder frequency (daily, weekly, monthly, one-time) |  | 2015-09-13 | Glenn | Unreviewed
Enter reminder text |  | 2015-09-13 | Glenn | Unreviewed
Select date for first email |  | 2015-09-13 | Glenn | Unreviewed
Display message after reminder is created |  | 2015-09-13 | Glenn | Unreviewed
Send email confirmation after reminder is created
Create an account |  | 2015-09-22 | Glenn |  |  | Hours Worked Per Day 13: 1; Hours Worked Per Day 22: 2
Enter email address |  | 2015-09-22 | Glenn
Enter password |  | 2015-09-22 | Glenn
Upload picture (optional) | [23 empty] | Color codes
Display confirmation message after account is created |  | 2015-09-22 | Glenn | [20 empty] | Finished
Send email confirmation after account is created | [23 empty] | In Progress
Sign into Reminder |  | 2015-09-21 | Glenn | Unreviewed | [19 empty] | Unreviewed | bar: Hours Worked Per Day 21
Email password reminder |  | 2015-09-21 | Glenn | Unreviewed | [19 empty] | Moved to 2nd Iteration | bar: Hours Worked Per Day 21
View your reminders |  | 2015-09-14 | Alexander | Unreviewed | 2015-09-17 | Hours Worked Per Day 15: 1,5; Hours Worked Per Day 16: 2; Hours Worked Per Day 17: 2
Reminder frequency |  | 2015-09-14 | Alexander | Unreviewed | 2015-09-17 | Hours Worked Per Day 16: 0,2; Hours Worked Per Day 17: 0,2
Reminder text |  | 2015-09-14 | Alexander | Unreviewed | 2015-09-17 | Hours Worked Per Day 16: 0,2; Hours Worked Per Day 17: 0,2
Date for first email |  | 2015-09-14 | Alexander | Unreviewed | 2015-09-17 | Hours Worked Per Day 16: 0,2; Hours Worked Per Day 17: 0,2
Edit your reminders |  | 2015-09-17 | Alexander |  |  | Hours Worked Per Day 17: 1; Hours Worked Per Day 21: 2; Hours Worked Per Day 22: 1
Reminder frequency |  | 2015-09-17 | Alexander
Reminder text |  | 2015-09-17 | Alexander
Date for first email |  | 2015-09-17 | Alexander
Display message after reminder is editted |  | 2015-09-17 | Alexander
Send email confirmation after reminder is editted
Delete your reminders |  | 2015-09-17 | Glenn | Unreviewed |  | Hours Worked Per Day 16: 0,5
Display message after reminder is deleted |  | 2015-09-17 | Glenn | Unreviewed |  | Hours Worked Per Day 16: 0,5
Send email confirmation after reminder is deleted |  | 2015-09-17
Create test cases for application |  | 2015-09-23 | Alexander | Unreviewed |  | Hours Worked Per Day 23: 2
Create description of application structure and setup |  | 2015-09-23 | Alexander | Unreviewed |  | Hours Worked Per Day 23: 1,5